## Step 1. Prepare
STEP 1 - Prepare
TO DO -- Confirm Sponsor -- Form Change Team: Project Leader, Communications, Area Leaders -- Agree on: Case for Change, Change Objectives, Success Measures, Communications Plan, Stakeholder Registry
Date: | Change Project: |  |  | Project Leader:
Sponsor: |  |  |  | Change Leader:
Understand the Change Goal: Articulate the change and why it is needed. Identify stakeholders.
What is changing and when?
Why is the change happening? (business need, case for change)
What will success look like?
Who is Impacted by this change? (list below)
Stakeholder Areas/Work Units:
Stakeholder Individuals:
Impacrted stakeholders in other areaws;
Others:
Understand the Impact Goal: Understand the specific changes and their magnitude for each stakeholder
Who is Impacted? |  | What is Changing? |  | How Big is This Change?
List each stakeholder (from above) |  | List each change for each stakeholders, Consider all aspects: roles, location, mindset/behaviors, reporting structures, processes, systems/tools, etc. Will it be a transitioned or cut-off change? |  | Impact of the change: 1 = Minor; 2 = Moderate; 3 = Major | 2000
Start Communicating and Listening Goal: Decide on format for acknowledging and communicating initial information about the change
Message | Audience |  | Format | From
Determine main points of the change | Should all stakeholders receive initial messages? |  | What format will the message take (email, meeting, etc.) | Who will deliver the message?

## Alt Stakeholder Reg
Stakeholder Registry
Groups (and/or Individuals) | Points of Contact | Training Needs | Anticipated Resistance/Mitigation

## Step 2. Manage
STEP 2 - Manage
TO DO -- Involve Leaders/Champions -- Schedule & Hold Trainings -- Document Resistance & Mitigation Plans -- Confirm Communications Plan -- Communicate & Listen -- Adjust as Needed
Date: | Change Project: |  |  |  | Leader:
Sponsor: |  |  |  |  | Change Leader:
What Trainings Are Needed?
What is Changing? | Who Needs Training? | Training Coordinator | Due Date | Training Resource
What new/enhanced skills are needed for new processes, systems, tools, equipments? | List each unit or stakeholder who needs to be trained | Who will schedule the training and ensure it is completed? | When must the training be completed? | How will the training be conducted? List the resource and training contact.
Resistance and Mitigation Goal: Plan for mitigation of challenges to stakeholders’ desire to support and participate in the change.
Anticipated Resistance |  |  | Mitigation Plans
List stakeholders and anticipated resistance (ex. reluctance/fear of new tech, lack of trust) |  |  | What action(s) should be taken to mitigate specific resistance? (ex.adjustments to trainings, more detailed communications, increased transparency)
Tailor Communications (or use separate Communications Plan template) Goal: To plan for timely and relevant communications with all stakeholders to ensure stakeholders' desire to support and participate in the change. Note: Depending on the level and scope of the change consider coordinating with school/unit communications team prior to creating a communications plan to ensure messaging is coordinated with campus and senior leadership in the school/unit.
Message | Audience |  | Messenger | Method | Timing (Due Date)
What needs to be communicated? | What stakeholders need to hear the message? |  | Who should deliver the message? | How should the message be delivered? Tip: High stakes messages are best delivered in-person (or zoom) | When should the message be delivered?

## Step 3. Reinforce
STEP 3 - Reinforce
TO DO -- Celebrate -- Measure Success -- Communicate & Listen -- Adjust as Needed -- Celebrate & Keep Listening
Date: | Change Project: |  |  | Leader:
Sponsor: |  |  |  | Change Leader:
Measure Success Use qualitative and quantative measures
What | Method | Stakeholder(s) | Who is Responsible? | Due Date
What aspect of the change are you measuring? | How will you measure it? | Who will be included? | Who will be responsible for the action? | Target date of measurement
Reinforcement Actions Needed Based on success measures, sustain the new behavior / performance until it is no longer considered a change
Action Owner | Action | Stakeholder(s) | One-Time or Recurring? | Due Date
Who will be responsible for taking this action? | What reinforcing action(s) will be taken? | Who are the stakeholders this action is intended to impact? | Will this action occur once or is it intended to be recurring (if so, how often)? | What date is the reinforcing action due?
3

## Lessons Learned - Optional
Lessons Learned Worksheet
Date: | Change Project: | Leader:
Sponsor: |  | Change Leader:
Lessons Learned Worksheet Goal: Reflect on anything that may be helpful for future organizational changes.
What went well in this change?
What needed improvement?
What would you do differently if you were to do a similar change in the future?