## Project Plan
Goal | Sub Goal | Staff Workforce Planning Template Step | Task | Responsible | Due Date | Status | Data Entry
PHASE 1
1 |  |  | Initial Data Collection (Pre-Work)
| 1 |  | Collect staff information by department (staff list; leaders; AVC, notations of union positions, in-place work agreements and accommodations). | Human Resources
| 2 |  | Identify Individual Roles (Initial estimation) | Human Resources |  |  | *
| 3 |  | Create burndown curve data (Chart) & summary table | Human Resources
2 |  |  | Develop Change Management and Communications Plans
| 1 |  | Use HR Change Management guidelines/template to create unit plan. | Change or Communications Manager
| 2 |  | Develop a Communications Plan to complement the Change Management Plan | Change or Communications Manager
| 3 |  | Create a "what to expect" email for employees. | Change or Communications Manager
| 4 |  | Create a "what to expect" email for leaders who will be involved in the project meetings | Change or Communications Manager
| 5 |  | Send "what to expect" emails | Project Manager
| 6 |  | Schedule recurring progress and milestone updates with Unit VC, AVCs, and Senior Leadership throughout the project (ex. Monday morning meetings). | Project Admin
3 |  |  | Pre-Meeting Discussions / Data Cleanup
| 1 |  | Conduct pre-meetings with Senior Leadership to: Review and confirm staff data; identify unique roles for each department; determine how far down within department leadership checklist discussions will occur; and preview template and checklist | Project Manager
| 2 |  | Enter final unique role data into unit master spreadsheet | Project Manager |  |  | *
| 3 |  | Pre-populate checklists for each department (one checklist for unique role - Project Manager will "save as" to create checklist for each employee in the role while conducting the meetings with managers) | Project Admin
4 |  |  | Project Plan Approval
| 1 |  | HRBP to obtain Approval of Unit Project Plan Concept | Dean / VC
| 2 |  | Present the Unit "Return-to-Work Staff Workforce Model" project plan to Unit Senior Leadership. Emphasize importance of objectivity, equity, and fairness, change management, and communications. | Project Manager
5 |  |  | Form Return to Work Team
| 1 |  | Form Unit Return to Work Team: Project Sponsor; Project Manager; Facilities Manager; IT; Purchasing; HR; and representative from one physical location (individual can represent dual roles provided they understand how to accomplish the tasks - example, one person may serve as physical location representative, purchasing and facilities) | Project Manager
| 2 |  | Identify and designate a point person to coordinate logistics for each physical location. This indivdual will coordinate timing, space and technology needs for new workplace models. | Return to Work Project Manager
PHASE 2
|  |  | STAFF WORKFORCE PLANNING TEMPLATE | Staff Workforce Planning Guidelines
6 |  |  | Staff Workforce Planning Template: Step 1a Identify Department Mission, Objectives, Services, Services Hours | Staff Workforce Planning Template
| 1 | 1a | As requested in "what to expect" email to leaders (steps 2.4 and 2.5), identify department's mission, objectives, services, service hours. Document it on the "Staff Workforce Planning Template". | Department Leader
| 2 | 1a | Submit Step 1a to Unit Return to Work Project Manager (this will be used while drafting departmental remote-eligibility checklists in the next step) | Department Leader
7 |  |  | Step 1b, Pre-Work: Staff Remote Criteria Checklists for each Department | Staff Remote Work Checklist
| 1 | 1b (pre-work) | Schedule meetings with department leaders who have been identified in step 3.1 to complete "remote criteria checklist". | Project Admin
| 2 | 1b (pre-work) | Meet with department leaders from step 3.1 to complete one "remote critera checklist" for each employee and discuss any questions utilizing the "questions to consider" in Step 1.a. (reference: Planning Guidelines). | Project Manager
| 3 | 1b (pre-work) | Follow-up and report back on any ideas or questions raised during meetings | Project Manager
| 4 | 1b (pre-work) | Document "remote critera checklist" responses on the unit master spreadsheet | Project Manager |  |  | *
| 5 | 1b (pre-work) | Review and discuss data with unit HR. Identify missing, outlying or concerning pieces of data, including gaps between discussions, issues raised and worksheet data. | Project Manager / HR
| 6 | 1b (pre-work) | Final Departmental Data Approval of partial / fully remote role eligibility | AVCs
| 7 | 1b (pre-work) | Refine data (if necessary) | Project Manager |  |  | *
| 8 | 1b (pre-work) | Approval of final list of preliminary remote-eligible roles (those that have not been deemed 100% onsite). | Dean / VC
8 |  |  | Staff Workforce Planning Template: Step 1b | Staff Workforce Planning Template
| 1 | 1b | Schedule meetings with identified department leaders (step 3.1 above) to facilitate completion of "Staff Planning Template, Step 1b" using the preliminary remote-eligible role list prepared above | Project Admin
| 2 | 1b | Conduct one meeting per department and facilitate completion of Step 1.b of the "Staff Planning Template" with each deaprtment leader. The Department's Mission, Objectives, Services, and Services Hours will be included in each template as a reference. Emphasize that this step is focused on each role and the department's needs rather than each staff member's performance, preferences, or needs. Utilize Questions to Consider in Step 1.b. and the Benefits and Challenges of Remote Work chart on Page 1 of the Planning Guidelines. Prompt the consideration of lessons-learned from the COVID-10 work-at-home model (ex. efficiencies, decreased absenteeism, staff engagement, etc.). | Project Manager
| 3 | 1b | Document and follow-up on ideas or questions raised and adjust documentation as needed | Project Manager
| 4 | 1b | Document data from Step 1.b meetings on unit master spreadsheet | Project Manager |  |  | *
| 5 | 1b | Report on progress to AVCs (if meetings occurred below that level) | Project Manager
| 6 | 1b | Report on progress to Unit Leadership | Project Manager / HRBP
9 |  |  | Change Management (Remote-Eligibility)
| 1 |  | Create talking points for department leaders to ensure timely and respectful discussions and communications with staff. Key talking points include: remote-eligibility outcomes (by role); preparing staff for the work location and equipment preference survey (next step). Additional tools: Sample language and mechanisms for feedback and two-way discussions. | Change or Communications Manager
| 2 |  | Create email to communicate forthcoming meetings regarding: remote-eligibility outcomes (by role); preparing staff for the work location and equipment preference survey (next step). | Change or Communications Manager
| 3 |  | Send all unit email to communicate forthcoming meetings regarding: remote-eligibility outcomes (by role); preparing remote-eligible staff for the work location and equipment preference survey (next step). | Change or Communications Manager
| 4 |  | Hold group or individual meetings to discuss remote eligibility outcomes (by role) and prepare staff for the work location and equipment preference survey (next step) | Department Managers
| 5 |  | Offer one-on-one meetings to discuss remote eligibility outcomes (by role) and respond to any questions / concerns. | Department Supervisors
10 |  |  | Step 2, Pre-Work: Work Location and Equipment Preference Surveys | Work Location & Equipment Preference Survey
| 1 | 2 (pre-work) | Utilizing the Work Location and Equipment Preference Survey sample, create customized survey to determine employee preferences for remote-eligible staff | Project Manager
| 2 | 2 (pre-work) | Deploy survey to remote-eligible employees; ensure expectations about budget are managed in email to employees | Project Manager
| 3 | 2 (pre-work) | Record survey responses in master data spreadsheet (not created yet - TBD based on survey) | Project Manager |  |  | *
| 4 | 2 (pre-work) | Review survey results with AVCs (if meetings occurred below that level) | Project Manager
| 5 | 2 (pre-work) | Present summary survey results to AVCs | Project Manager
11 |  |  | Staff Workforce Planning Template: Step 2 | Staff Workforce Planning Template
| 1 | 2 | Meet with department leaders to identify how to stagger staff work schedules to leverage the use of office space. Determinations should be based on unit / department business need, then staff preferences. | Project Manager
| 2 | 2 | Create a revised floorplan with current number of offices; workstations; hoteling spaces in each department. | Project Manager
| 3 | 2 | Document staff schedule data on master spreadsheet | Project Manager |  |  | *
| 4 | 2 | Review results with department roll-up leaders | Project Manager
| 5 | 2 | Present summary results to AVCs (if meetings occurred below that level) | Project Manager
| 6 | 2 | Approval of revised work schedules and floorplans | Vice Chancellor
| 7 | 2 | Provide revised workschedules and floorplans to Return Onsite Project Manager for planning purposes | Project Manager
12 |  |  | Staff Workforce Planning Template: Steps 3 & 4 | Staff Workforce Planning Template
| 1 | 3 & 4 | Email Draft (Partially Completed, Steps 1-2) Staff Workforce Planning Templates and homework request to Leaders. Homework Request: Review steps 3 and 4 of Staff Workforce Planning Template in preparation for group meeting. Draft and return to Unit Change Management Lead for use in Group Meeting. (How leaders will lead their staff in the new workforce model. Utilize HR tips for leading a Hybrid Workforce resources, reimagine the employee experience, and how to adapt as a leader.) | Change Manager
| 2 | 3 & 4 | Conduct Group Meeting with Leaders for the purpose of sharing/exchanging ideas and best practices (step 3) and gaining buy-in on step 4 (stakeholders/key messages), ensuring no oversights. | Change Manager
| 3 | 3 & 4 | Document final language for departmental Staff Workforce Planning Template (Steps 3 & 4). Submit completed document to Project Manager | Department Leader
| 4 | 4 | Compile information received in group meeting. Draft unit-level change management and communications approach to bringing staff into the new workforce model (including onsite). Tools include: Sample language for group meetings, one-on-one meeting, and email communications; sample language and mechanisms for feedback and two-way discussions. | Change or Communications Manager
13 |  |  | Complete Workforce Model
| 1 | 4 | Complete Unit workforce model project summary and proposed workplace model proposals for all departments. Confirm with HR and all appropriate roll-up leaders. | Project Manager
| 2 | 4 | Present Unit workforce model project summary and proposed workplace model proposals to VC and AVCs & obtain approvals | Project Manager
| 3 | 4 | 1st Level Approval of Departmental Workforce Models | AVCs
| 4 | 4 | 2nd Level Approval of Departmental Workforce Models | Vice Chancellor
| 5 | 4 | Approval of Overall Unit Workforce Model | Vice Chancellor
| 6 | 4 | Execute Change Management Plan (from Step 12.2 above) | Change Manager
| 7 | 4 | Submit Approved Staff Workforce Models to Project Manager | Vice Chancellor
PHASE 3
14 |  |  | Implement the New Workforce Model | Staff Remote Work Guidelines & Agreement
| 1 |  | Submit copies of approved workforce models to Return to Work Project Manager | Project Manager
| 2 |  | Create list of Staff Remote Work Agreements Needed | Project Admin
| 3 |  | Update and track remote work agreements in unit master spreadsheet | Project Admin
15 |  |  | Change Management (Monitor and Adjust)
| 1 |  | Draft change management and communications tools to monitor effectiveness of new workforce model including: Sample language for group meetings, one-on-one meeting, and email communications; sample language and mechanisms for feedback and two-way discussions. | Change or Communications Manager
| 2 |  | Implement tools to empower staff to share feedback | All Leaders
| 3 |  | Encourage leaders to observe staff adoption of changes and effectiveness of new workforce model | Change or Communications Manager
| 4 |  | Continue communicating and discussing workforce model and outcomes with staff and leadership | Change or Communications Manager

## Data Master Spreadsheet
Employee Name | Department | Leader | Title Name | Unique Role | Remote Checklist | Location | FLSA | Union | 1b) PreWork Remote Eligible? | 1b) Workforce Composition | Current Workspace | New Workspace
| A2 |  |  | 1 | 1 | Diagon Alley | N | 99 | Fully | Remote | Workstation | Hoteling
| A2 |  |  | 1 | 1 | Diagon Alley | E | 99 | Fully | 3+ Onsite | Workstation | Shared Workspace
| A2 |  |  | 1 | 1 | Diagon Alley | E | 99 | Fully | 3+ Onsite | Workstation | Shared Workspace
| A2 |  |  | 1 | 1 | Diagon Alley | E | 99 | Fully | 3+ Onsite | Workstation | Shared Workspace
| A2 |  |  | 1 | 1 | Diagon Alley | E | 99 | Fully | 3+ Onsite | Workstation | Shared Workspace
| A2 |  |  | 1 | 1 | Diagon Alley | E | 99 | Fully | 3+ Onsite | Office | Shared Workspace
| A2 |  |  | 1 | 1 | Diagon Alley | E | 99 | Fully | 3+ Onsite | Workstation | Shared Workspace
| A2 |  |  | 1 | 1 | Diagon Alley | E | 99 | Fully | 3+ Onsite | Office | Shared Workspace
| A2 |  |  | 1 | 1 | Diagon Alley | N | 99 | Fully | 3+ Onsite | Workstation | Shared Workspace
| A2 |  |  | 1 | 1 | Diagon Alley | E | 99 | Fully | Onsite | Workstation | Shared Workspace
| A2 |  |  | 1 | 1 | Diagon Alley | N | 99 | Fully | 3+ Onsite | Workstation | Hoteling
| A2 |  |  | 1 | 1 | Diagon Alley | N | 99 | Fully | 3+ Onsite | Workstation | Hoteling
| A2 |  |  | 1 | 1 | Diagon Alley | N | 99 | Fully | 3+ Onsite | Workstation | Hoteling
| A2 |  |  | 1 | 1 | Diagon Alley | E | 99 | Fully | 3+ Onsite | Workstation | Shared Workspace
| A2 |  |  | 1 | 1 | Hogwarts | E | 99 | Fully | 3+ Onsite | Office | Office
| B |  |  | 1 | 1 | Hogwarts | E | HX | Fully | 3+ Onsite | Workstation | Workstation
| B |  |  | 0 | 1 | Hogwarts | E | HX | Fully | 3+ Onsite | Workstation | Workstation
| B |  |  | 1 | 1 | Hogwarts | E | 99 | Fully | 3+ Onsite | Office | Office
| B |  |  | 1 | 1 | Hogwarts | N | 99 | Fully | 3+ Onsite | Workstation | Shared Workspace
| B |  |  | 0 | 1 | Hogwarts | N | 99 | Fully | 3+ Onsite | Workstation | Shared Workspace
| C |  |  | 1 | 1 | Hogwarts | N | 99 | Fully | 3+ Onsite | Workstation | Shared Workspace
| C |  |  | 1 | 1 | Hogwarts | N | 99 | Fully | Onsite | Workstation | Shared Workspace
| C |  |  | 0 | 1 | Hogwarts | E | 99 | Fully | 3+ Onsite | Office | Hoteling
| C |  |  | 1 | 1 | Gryffindor | E | 99 | Fully | 3+ Onsite | Office | Office
| C |  |  | 1 | 1 | Gryffindor | E | 99 | Fully | 3+ Onsite | Office | Office
| C |  |  | 1 | 1 | Gryffindor | E | 99 | Fully | 3+ Onsite | Office | Hoteling
| C |  |  | 1 | 1 | Gryffindor | E | 99 | Fully | 3+ Onsite | Office | Office
| C |  |  | 1 | 1 | Gryffindor | N | 99 | Fully | 3+ Onsite | Workstation | Workstation
| C |  |  | 1 | 1 | Gryffindor | N | 99 | Fully | 3+ Onsite | Workstation | Shared Workspace
| D4 |  |  | 1 | 1 | Hogwarts | N | 99 | Ineligible | Onsite | Workstation | Shared Workspace
| D4 |  |  | 1 | 1 | Hogwarts | E | 99 | Ineligible | Onsite | Office | Office
| D4 |  |  | 1 | 1 | Hogwarts | N | 99 | Fully | 3+ Onsite | Workstation | Office
| D4 |  |  | 1 | 1 | Hogwarts | E | 99 | Fully | 3+ Onsite | Workstation | Office
| D4 |  |  | 1 | 1 | Hogwarts | E | 99 | Fully | 3+ Onsite | Office | Office
| D4 |  |  | 1 | 1 | Hogwarts | E | 99 | Fully | 3+ Onsite | Office | Office
| D4 |  |  | 1 | 1 | Hogwarts | E | 99 | Fully | 3+ Onsite | Office | Shared Workspace
| D4 |  |  | 1 | 1 | Gryffindor | E | 99 | Fully | 3+ Onsite | Office | Office
| E2 |  |  | 1 | 1 | Gryffindor | E | 99 | Fully | 3+ Onsite | Workstation | Shared Workspace
| E2 |  |  | 1 | 1 | Gryffindor | E | 99 | Fully | 3+ Onsite | Office | Shared Workspace
| E2 |  |  | 1 | 1 | Gryffindor | E | 99 | Fully | 3+ Onsite | Workstation | Office
| E2 |  |  | 1 | 1 | Gryffindor | E | 99 | Ineligible | 3+ Onsite | Workstation | Office
| E2 |  |  | 1 | 1 | Gryffindor | E | 99 | Ineligible | Remote | Office | Hoteling
| F20 |  |  | 1 | 1 | Gryffindor | E | 99 | Ineligible | 3+ Onsite | Workstation | Hoteling
| F20 |  |  | 1 | 1 | Gryffindor | E | 99 | Ineligible | 3+ Onsite | Workstation | Hoteling
| F20 |  |  | 1 | 1 | Gryffindor | E | 99 | Ineligible | 3+ Onsite | Workstation | Hoteling
| F20 |  |  | 1 | 1 | Gryffindor | E | 99 | Ineligible | 3+ Onsite | Office | Hoteling
| F20 |  |  | 1 | 1 | Hogwarts | E | 99 | Ineligible | 3+ Onsite | Office | Hoteling
| F20 |  |  | 1 | 1 | Hogwarts | E | 99 | Ineligible | 3+ Onsite | Office | Hoteling
| F20 |  |  | 1 | 1 | Hogwarts | E | 99 | Ineligible | 3+ Onsite | Office | Hoteling
| F20 |  |  | 1 | 1 | Hogwarts | E | 99 | Ineligible | 3+ Onsite | Office | Hoteling
| F20 |  |  | 1 | 1 | Hogwarts | E | 99 | Ineligible | 3+ Onsite | Office | Hoteling
| F20 |  |  | 1 | 1 | Hogwarts | E | 99 | Ineligible | 3+ Onsite | Workstation | Hoteling
| F20 |  |  | 1 | 1 | Hogwarts | E | 99 | Ineligible | 3+ Onsite | Workstation | Hoteling
| F20 |  |  | 1 | 1 | Hogwarts | E | 99 | Ineligible | 3+ Onsite | Office | Hoteling
| G |  |  | 1 | 1 | Hogwarts | E | 99 | Ineligible | Onsite | Office | Hoteling
| G |  |  | 1 | 1 | Hogwarts | N | 99 | Ineligible | Onsite | Workstation | Hoteling
| G |  |  | 1 | 1 | Diagon Alley | E | 99 | Ineligible | Onsite | Office | Hoteling
| G |  |  | 1 | 1 | Diagon Alley | N | 99 | Ineligible | Onsite | Workstation | Hoteling
| G |  |  | 1 | 1 | Diagon Alley | E | 99 | Ineligible | Onsite | Office | Hoteling
| G |  |  | 1 | 1 | Diagon Alley | E | 99 | Ineligible | Onsite | Office | Hoteling
| G |  |  | 1 | 1 | Diagon Alley | N | 99 | Ineligible | Onsite | Office | Hoteling
| G |  |  | 1 | 1 | Diagon Alley | N | CX | Partial | 3+ Onsite | Workstation | Hoteling
| G |  |  | 1 | 1 | Diagon Alley | N | 99 | Partial | 3+ Onsite | Workstation | Hoteling
| G |  |  | 1 | 1 | Diagon Alley | E | 99 | Partial | 3+ Onsite | Office | Office
| G |  |  | 1 | 1 | Diagon Alley | E | 99 | Partial | 3+ Onsite | Workstation | Workstation
| G |  |  | 1 | 1 | Diagon Alley | E | 99 | Partial | 3+ Onsite | Workstation | Hoteling
| G |  |  | 0 | 1 | Diagon Alley | E | 99 | Partial | 3+ Onsite | Workstation | Hoteling
| G |  |  | 1 | 1 | Gryffindor | E | 99 | Partial | 3+ Onsite | Office | Office
| G |  |  | 1 | 1 | Gryffindor | E | 99 | Partial | 3+ Onsite | Office | Office
| H |  |  | 1 | 1 | Gryffindor | N | 99 | Partial | 3+ Onsite | Workstation | Workstation
| H |  |  | 0 | 1 | Gryffindor | N | 99 | Partial | 3+ Onsite | Workstation | Workstation
| H |  |  | 0 | 1 | Gryffindor | N | 99 | Partial | 3+ Onsite | Workstation | Workstation
| H |  |  | 0 | 1 | Gryffindor | N | 99 | Partial | 3+ Onsite | Workstation | Workstation
| H |  |  | 1 | 1 | Gryffindor | E | 99 | Partial | 3+ Onsite | Workstation | Workstation
| H |  |  | 1 | 1 | Gryffindor | E | 99 | Partial | Onsite | Workstation | Workstation
| H |  |  | 1 | 1 | Gryffindor | E | 99 | Partial | 3+ Onsite | Workstation | Workstation
| H |  |  | 1 | 1 | Gryffindor | E | 99 | Partial | 3+ Onsite | Office | Office
| H |  |  | 1 | 1 | Gryffindor | E | 99 | Partial | 3+ Onsite | Workstation | Workstation
| H |  |  | 1 | 1 | Gryffindor | E | 99 | Partial | 3+ Onsite | Office | Office
| H |  |  | 1 | 1 | Gryffindor | E | 99 | Partial | 3+ Onsite | Office | Office
| H |  |  | 1 | 1 | Gryffindor | E | 99 | Partial | 3+ Onsite | Office | Office
| H |  |  | 1 | 1 | Gryffindor | N | CX | Partial | 3+ Onsite | Workstation | Workstation
| H |  |  | 1 | 1 | Gryffindor | E | 99 | Partial | 3+ Onsite | Workstation | Workstation
| H |  |  | 1 | 1 | Gryffindor | E | 99 | Partial | Onsite | Office | Office
| I |  |  | 1 | 1 | Gryffindor | N | CX | Partial | 1-2 Onsite | Workstation | Workstation
| I |  |  | 1 | 1 | Gryffindor | N | 99 | Partial | 3+ Onsite | Workstation | Workstation
| I |  |  | 0 | 1 | Gryffindor | N | 99 | Partial | 3+ Onsite | Workstation | Workstation
| I |  |  | 0 | 1 | Gryffindor | N | 99 | Partial | 3+ Onsite | Workstation | Workstation
| I |  |  | 1 | 1 | Gryffindor | E | 99 | Partial | 3+ Onsite | Office | Office
| I |  |  | 1 | 1 | Gryffindor | E | 99 | Partial | 3+ Onsite | Office | Office
| I |  |  | 0 | 1 | Gryffindor | E | 99 | Partial | 3+ Onsite | Office | Office
| I |  |  | 0 | 1 | Gryffindor | E | 99 | Partial | 3+ Onsite | Office | Office
| I |  |  | 0 | 1 | Hogwarts | N | CX | Partial | 3+ Onsite | Workstation | Workstation
| I |  |  | 1 | 1 | Hogwarts | N | 99 | Partial | 3+ Onsite | Workstation | Workstation
| I |  |  | 1 | 1 | Hogwarts | E | 99 | Partial | 3+ Onsite | Workstation | Workstation
| I |  |  | 0 | 1 | Hogwarts | N | 99 | Partial | 3+ Onsite | Workstation | Workstation
| I |  |  | 0 | 1 | Hogwarts | N | 99 | Partial | 3+ Onsite | Workstation | Workstation
| I |  |  | 0 | 1 | Hogwarts | E | 99 | Partial | 3+ Onsite | Office | Workstation
| I |  |  | 1 | 1 | Hogwarts | E | 99 | Partial | 3+ Onsite | Office | Office
| I |  |  | 0 | 1 | Hogwarts | E | 99 | Partial | 3+ Onsite | Office | Office
| I |  |  | 0 | 1 | Hogwarts | E | 99 | Partial | 3+ Onsite | Office | Shared Workspace
| I |  |  | 0 | 1 | Hogwarts | E | 99 | Partial | 3+ Onsite | Office | Office
| I |  |  | 1 | 1 | Hogwarts | E | 99 | Partial | 3+ Onsite | Office | Office
| I |  |  | 1 | 1 | Hogwarts | E | 99 | Partial | 3+ Onsite | Office | Office
| I |  |  | 1 | 1 | Hogwarts | E | 99 | Partial | 3+ Onsite | Office | Office
| I |  |  | 0 | 1 | Hogwarts | N | CX | Partial | 3+ Onsite | Workstation | Workstation
| I |  |  | 1 | 1 | Hogwarts | E | 99 | Partial | 3+ Onsite | Office | Workstation
| I |  |  | 0 | 1 | Hogwarts | N | 99 | Partial | 3+ Onsite | Workstation | Workstation
| I |  |  | 0 | 1 | Hogwarts | N | 99 | Partial | 3+ Onsite | Workstation | Workstation
| I |  |  | 0 | 1 | Hogwarts | N | 99 | Partial | 3+ Onsite | Workstation | Workstation
| I |  |  | 1 | 1 | Hogwarts | N | 99 | Partial | 3+ Onsite | Workstation | Workstation
| I |  |  | 0 | 1 | Hogwarts | E | 99 | Partial | 3+ Onsite | Office | Shared Workspace
| I |  |  | 0 | 1 | Hogwarts | E | 99 | Partial | 3+ Onsite | Office | Shared Workspace
| I |  |  | 0 | 1 | Hogwarts | E | 99 | Partial | 3+ Onsite | Office | Shared Workspace
| I |  |  | 0 | 1 | Hogwarts | E | 99 | Partial | 3+ Onsite | Office | Shared Workspace
| I |  |  | 0 | 1 | Hogwarts | E | 99 | Partial | 3+ Onsite | Office | Shared Workspace
| I |  |  | 0 | 1 | Hogwarts | E | 99 | Partial | 3+ Onsite | Office | Shared Workspace
| I |  |  | 0 | 1 | Hogwarts | E | 99 | Partial | 3+ Onsite | Office | Office
| J |  |  | 1 | 1 | Hogwarts | N | CX | Partial | 3+ Onsite | Workstation | Workstation
| J |  |  | 1 | 1 | Hogwarts | N | 99 | Partial | 3+ Onsite | Workstation | Shared Workspace
| J |  |  | 1 | 1 | Hogwarts | E | 99 | Partial | 3+ Onsite | Workstation | Shared Workspace
| J |  |  | 1 | 1 | Gryffindor | E | 99 | Partial | 3+ Onsite | Workstation | Shared Workspace
| J |  |  | 1 | 1 | Gryffindor | E | 99 | Partial | Onsite | Office | Hoteling
| J |  |  | 1 | 1 | Gryffindor | E | 99 | Partial | 3+ Onsite | Workstation | Shared Workspace
| K |  |  | 1 | 1 | Gryffindor | E | 99 | Partial | Onsite | Workstation | Office
| K |  |  | 1 | 1 | Gryffindor | E | 99 | Partial | 3+ Onsite | Workstation | Office
| K |  |  | 1 | 1 | Gryffindor | N | 99 | Partial | Onsite | Workstation | Shared Workspace
| K |  |  | 1 | 1 | Gryffindor | N | 99 | Partial | Remote | Workstation | Shared Workspace
| K |  |  | 0 | 1 | Gryffindor | N | 99 | Partial | Remote | Workstation | Shared Workspace
| K |  |  | 0 | 1 | Gryffindor | N | 99 | Partial | Remote | Workstation | Shared Workspace
| K |  |  | 1 | 1 | Gryffindor | N | 99 | Partial | Remote | Workstation | Shared Workspace
| K |  |  | 1 | 1 | Gryffindor | E | 99 | Partial | Remote | Workstation | Shared Workspace
| K |  |  | 0 | 1 | Gryffindor | E | 99 | Partial | Remote | Office | Shared Workspace
| K |  |  | 0 | 1 | Gryffindor | E | 99 | Partial | Remote | Office | Shared Workspace
| L |  |  | 1 | 1 | Gryffindor | N | 99 | Partial | 3+ Onsite | Workstation | Workstation
| L |  |  | 1 | 1 | Gryffindor | E | 99 | Partial | 3+ Onsite | Office | Shared Workspace
| L |  |  | 0 | 1 | Gryffindor | E | 99 | Partial | 3+ Onsite | Office | Shared Workspace
| L |  |  | 1 | 1 | Hogwarts | E | 99 | Partial | 3+ Onsite | Office | Office
| M |  |  | 1 | 1 | Hogwarts | E | 99 | Partial | 3+ Onsite | Office | Office
| M |  |  | 1 | 1 | Hogwarts | N | 99 | Partial | 3+ Onsite | Workstation | Shared Workspace
| M |  |  | 1 | 1 | Hogwarts | E | 99 | Partial | 3+ Onsite | Workstation | Shared Workspace
| M |  |  | 0 | 1 | Hogwarts | E | 99 | Partial | 3+ Onsite | Workstation | Shared Workspace
| M |  |  | 0 | 1 | Hogwarts | E | 99 | Partial | 3+ Onsite | Workstation | Shared Workspace
| M |  |  | 0 | 1 | Diagon Alley | E | 99 | Partial | 3+ Onsite | Workstation | Shared Workspace
| M |  |  | 1 | 1 | Diagon Alley | E | 99 | Partial | 3+ Onsite | Workstation | Shared Workspace
| M |  |  | 1 | 1 | Diagon Alley | E | 99 | Partial | 3+ Onsite | Office | Workstation
| N |  |  | 1 | 1 | Diagon Alley | N | 99 | Partial | 3+ Onsite | Workstation | Shared Workspace
| N |  |  | 1 | 1 | Diagon Alley | N | 99 | Ineligible | 3+ Onsite | Workstation | Shared Workspace
| N |  |  | 1 | 1 | Diagon Alley | E | 99 | Ineligible | 3+ Onsite | Office | Shared Workspace
| O |  |  | 1 | 1 | Diagon Alley | N | CX | Ineligible | 3+ Onsite | Workstation | Workstation
| O |  |  | 1 | 1 | Diagon Alley | E | 99 | Ineligible | 3+ Onsite | Workstation | Shared Workspace
| P |  |  | 1 | 1 | Diagon Alley | E | 99 | Ineligible | 3+ Onsite | Office | Office
| P |  |  | 1 | 1 | Diagon Alley | E | 99 | Ineligible | Onsite | Office | Shared Workspace
| P |  |  | 1 | 1 | Diagon Alley | E | 99 | Ineligible | Remote | Office | Office

## Burndown Input
| # Roles | Week 1 | Week 2 | Week 3 | Week 4
Remaining Conversations | 154 | 154 | 154 | 154 | 154
Total Conversations | 154 | 115.5 | 77 | 38.5 | 0
Department | # of Roles | Week 1 | Week 2 | Week 3 | Week 4 | Completed Conversations | Remaining Conversations | Department | Leader 1 | Leader 2 | Leader 4 | Leader 4
A2 | 15 | 0 | 0 | 0 | 0 | 0 | 15 | A2 | 1A
B | 5 | 0 | 0 | 0 | 0 | 0 | 5 | B | 1B
C | 9 | 0 | 0 | 0 | 0 | 0 | 9 | C | 1C
D4 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | D4 | 1D
E2 | 5 | 0 | 0 | 0 | 0 | 0 | 5 | E2 | 1E
F20 | 12 | 0 | 0 | 0 | 0 | 0 | 12 | F20 | 1F
G | 15 | 0 | 0 | 0 | 0 | 0 | 15 | G | 1G
H | 15 | 0 | 0 | 0 | 0 | 0 | 15 | H | 1H
I | 34 | 0 | 0 | 0 | 0 | 0 | 34 | I | 1I
J | 6 | 0 | 0 | 0 | 0 | 0 | 6 | J | 1J
K | 10 | 0 | 0 | 0 | 0 | 0 | 10 | K | 1K
L | 4 | 0 | 0 | 0 | 0 | 0 | 4 | L | 1L
M | 8 | 0 | 0 | 0 | 0 | 0 | 8 | M | 1M
N | 3 | 0 | 0 | 0 | 0 | 0 | 3 | N | 1N
O | 2 | 0 | 0 | 0 | 0 | 0 | 2 | O | 1O
P | 3 | 0 | 0 | 0 | 0 | 0 | 3 | P | 1P
Total Conversations | 154 | 0 | 0 | 0 | 0 | 0 | 154

## 1b)Remote Eligibility
Count of 1b) PreWork Remote Eligible? | Column Labels
Row Labels | Fully | Ineligible | Partial | Grand Total
A2 | 15 |  |  | 15
B | 5 |  |  | 5
C | 9 |  |  | 9
D4 | 6 | 2 |  | 8
E2 | 3 | 2 |  | 5
F20 |  | 12 |  | 12
G |  | 7 | 8 | 15
H |  | 15 |  | 15
I |  | 34 |  | 34
J |  | 6 |  | 6
K |  | 10 |  | 10
L |  | 4 |  | 4
M |  | 8 |  | 8
N |  | 3 |  | 3
O |  | 2 |  | 2
P |  | 3 |  | 3
Grand Total | 38 | 108 | 8 | 154
Eligibility | Count | Percent
Fully | 38 | 24.68%
Ineligible | 30 | 19.48%
Partial | 86 | 55.84%
Grand Total | 154 | 100%

## 1b)Workforce Composition
Count of 1b) Workforce Composition | Column Labels
Row Labels | 1-2 Onsite | 3+ Onsite | Onsite | Remote | Grand Total
A2 |  | 13 | 1 | 1 | 15
B |  | 5 |  |  | 5
C |  | 8 | 1 |  | 9
D4 |  | 6 | 2 |  | 8
E2 |  | 4 |  | 1 | 5
F20 |  | 12 |  |  | 12
G |  | 8 | 7 |  | 15
H |  | 13 | 2 |  | 15
I | 1 | 33 |  |  | 34
J |  | 5 | 1 |  | 6
K |  | 1 | 2 | 7 | 10
L |  | 4 |  |  | 4
M |  | 8 |  |  | 8
N |  | 3 |  |  | 3
O |  | 2 |  |  | 2
P |  | 1 | 1 | 1 | 3
Grand Total | 1 | 126 | 17 | 10 | 154

## 2)Workspace Summary
Count of Current Workspace | Column Labels
Row Labels | Office | Workstation | Grand Total
A2 | 3 | 12 | 15
B | 1 | 4 | 5
C | 5 | 4 | 9
D4 | 5 | 3 | 8
E2 | 2 | 3 | 5
F20 | 7 | 5 | 12
G | 8 | 7 | 15
H | 5 | 10 | 15
I | 20 | 14 | 34
J | 1 | 5 | 6
K | 2 | 8 | 10
L | 3 | 1 | 4
M | 2 | 6 | 8
N | 1 | 2 | 3
O |  | 2 | 2
P | 3 |  | 3
Grand Total | 68 | 86 | 154
Count of New Workspace | Column Labels
Row Labels | Hoteling | Office | Shared Workspace | Workstation | Grand Total
A2 | 4 | 1 | 10 |  | 15
B |  | 1 | 2 | 2 | 5
C | 2 | 3 | 3 | 1 | 9
D4 |  | 6 | 2 |  | 8
E2 | 1 | 2 | 2 |  | 5
F20 | 12 |  |  |  | 12
G | 11 | 3 |  | 1 | 15
H |  | 5 |  | 10 | 15
I |  | 11 | 7 | 16 | 34
J | 1 |  | 4 | 1 | 6
K |  | 2 | 8 |  | 10
L |  | 1 | 2 | 1 | 4
M |  | 1 | 6 | 1 | 8
N |  |  | 3 |  | 3
O |  |  | 1 | 1 | 2
P |  | 2 | 1 |  | 3
Grand Total | 31 | 38 | 51 | 34 | 154
Count of Current Workspace | Column Labels
Row Labels | Office | Workstation | Grand Total
Diagon Alley | 12 | 24 | 36
Hogwarts | 32 | 29 | 61
Gryffindor | 24 | 33 | 57
Grand Total | 68 | 86 | 154
Count of New Workspace | Column Labels
Row Labels | Hoteling | Office | Shared Workspace | Workstation | Grand Total
Diagon Alley | 13 | 3 | 17 | 3 | 36
Hogwarts | 11 | 16 | 19 | 15 | 61
Gryffindor | 7 | 19 | 15 | 16 | 57
Grand Total | 31 | 38 | 51 | 34 | 154

## Burndown Instructions
Burndown Template
INSTRUCTIONS
Objective | Complete one checklist for each staff member in the unit.
Action | Step 1) Determine how many weeks you want to complete checklists Step 2) Add or remove "week" columns and update formula to reflect number of weeks from four if you plan to complete checklists over more or less than four weeks. Update the formulas in rows four and five of the burndown input worksheet.
What to complete | All fields where cells are shaded blue. Do not input into grey cells as this may result in an incorrect calculation.
Content Requirements | Name | Description
| Department | Update the departments you will track
| # of checklists | Number of checklists = one per staff member
| Weekly Entries | Enter the number of checklists / conversations that are completed each week until the department has completed conversations
| Completed Conversations | Automatically calculated based on number of conversations completed by week
| Remaining Conversations | Automatically calculated based on number of conversations completed by week
| Chart Contents | The chart will assume equal weekly effort for four weeks until other entries are made into the blue fields.

## DNU
Remote | Office | Office | Diagon Alley | Ineligible
Onsite | Workstation | Workstation | Hogwarts | Partial
3+ Onsite | Shared Workspace |  | Gryffindor | Fully
1-2 Onsite | Hoteling